## Sheet1
Unique ID | Phase | In Scope | Optional | Template vs Deployment | TMC 2020 | In Activate? | Ferring - Deployment | Ferring - Template | Biontech | Action | Responsible Team/Workstream | Description | Detailed Description | Waterfall / Agile | L3 | L4 | Activate Deliverables / Accelerators | TMC Deliverables / Accelerators | Implementation Type
New | Explore | Yes |  | Both |  | No |  |  |  |  | Project Management​ | Explore- Regular Phase Activities
3.070.010.000 | Explore | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Phase Initiation |  | Waterfall;#Agile | 10 | 0 |  |  | Brownfield;#Greenfield;#Bluefield
3.070.010.010 | Explore | Yes |  | Both | yes | Yes | yes |  |  |  | Project Management​ | Review Deliverables of Explore Phase |  | Waterfall;#Agile | 10 | 10 |  |  | Brownfield;#Greenfield;#Bluefield
3.070.010.020 | Explore | Yes |  | Both | yes | Yes | yes |  |  |  | Project Management​ | Review Acceptance Criteria |  | Waterfall;#Agile | 10 | 20 |  |  | Brownfield;#Greenfield;#Bluefield
3.070.010.030 | Explore | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Review RACI Chart for Explore Phase |  | Waterfall;#Agile | 10 | 30 |  |  | Brownfield;#Greenfield;#Bluefield
3.070.020.000 | Explore | Yes |  | Both | yes | Yes | yes |  |  |  | Project Management​ | Execution, Monitoring and Controlling Results | Set up WS alignment meetings , gap governance meetings | Waterfall;#Agile | 20 | 0 | BOM.131;#274;#PM.41;#317 |  | Brownfield;#Greenfield;#Bluefield
3.070.020.010 | Explore | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Update Project Management Plan |  | Waterfall;#Agile | 20 | 10 |  |  | Brownfield;#Greenfield;#Bluefield
3.070.020.020 | Explore | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Direct and Manage Project Execution |  | Waterfall;#Agile | 20 | 20 | AG.16;#228 |  | Brownfield;#Greenfield;#Bluefield
3.070.020.030 | Explore | Yes | Yes | Both | yes | Yes |  |  |  |  | Project Management​ | Conduct SCRUM Meetings |  | Agile | 20 | 30 | AG.19;#231 |  | Brownfield;#Greenfield;#Bluefield
3.070.020.040 | Explore | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Monitor and Control Project Activities |  | Waterfall;#Agile | 20 | 40 |  |  | Brownfield;#Greenfield;#Bluefield
3.070.020.050 | Explore | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Manage Issues, Risks and Changes |  | Waterfall;#Agile | 20 | 50 | PM.44;#318;#PM.45;#319 |  | Brownfield;#Greenfield;#Bluefield
3.070.020.060 | Explore | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Communicate Status and Progress to Project Stakeholders |  | Waterfall;#Agile | 20 | 60 | PM.41;#317 |  | Brownfield;#Greenfield;#Bluefield
3.070.410.000 | Explore | Yes |  | Both | yes | Yes | yes |  |  |  | Project Management​ | Phase Closure and Sign-Off phase Deliverables |  | Waterfall;#Agile | 410 | 0 |  |  | Brownfield;#Greenfield;#Bluefield
3.070.410.010 | Explore | not needed |  | Both | yes | Yes |  |  |  | remove | Project Management​ | Conduct Knowledge Management Gate |  | Waterfall;#Agile | 410 | 10 | PM.81;#322;#PM.80;#321 |  | Brownfield;#Greenfield;#Bluefield
3.050.320.000 | Explore |  |  | Both | yes | Yes |  |  |  |  | Integration | Integration Design |  | Waterfall;#Agile | 320 | 0 |  |  | Brownfield;#Greenfield;#Bluefield
3.050.320.010 | Explore |  |  | Both | yes | Yes |  |  |  |  | Integration | Define Interface Architecture |  | Waterfall;#Agile | 320 | 10 |  |  | Brownfield;#Greenfield;#Bluefield
Security Infrastructure is defined, derived roles concept has been developed, to be mapped to localisation requirements
5..000.000 | Deploy |  |  | Both | yes | Yes |  |  |  |  | All | Deploy |  | Waterfall;#Agile | 0 | 0
5.070.010.000 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Phase Initiation |  | Waterfall;#Agile | 10 | 0 | PM.01;#290 |  | Brownfield;#Greenfield;#Bluefield
5.070.010.010 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Allocate Resources and Update Project Schedule |  | Waterfall;#Agile | 10 | 10 |  |  | Brownfield;#Greenfield;#Bluefield
5.070.010.020 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Perform Kickoff Meeting |  | Waterfall;#Agile | 10 | 20 | PM.13;#295 |  | Brownfield;#Greenfield;#Bluefield
5.070.020.000 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Execution, Monitoring and Controlling Results |  | Waterfall;#Agile | 20 | 0 | BOM.131;#274;#PM.41;#317 |  | Brownfield;#Greenfield;#Bluefield
5.070.020.010 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Update Project Management Plan |  | Waterfall;#Agile | 20 | 10 |  |  | Brownfield;#Greenfield;#Bluefield
5.070.020.020 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Direct and Manage Project Execution |  | Waterfall;#Agile | 20 | 20 |  |  | Brownfield;#Greenfield;#Bluefield
5.070.020.030 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Monitor and Control Project Activities |  | Waterfall;#Agile | 20 | 30 |  |  | Brownfield;#Greenfield;#Bluefield
5.070.020.040 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Manage Issues, Risks and Changes |  | Waterfall;#Agile | 20 | 40 | PM.44;#318;#PM.45;#319 |  | Brownfield;#Greenfield;#Bluefield
5.070.020.050 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Communicate Status and Progress to Project Stakeholders |  | Waterfall;#Agile | 20 | 50 | PM.41;#317 |  | Brownfield;#Greenfield;#Bluefield
5.070.070.000 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Release Closing |  | Agile | 70 | 0 |  |  | Bluefield;#Brownfield;#Greenfield
5.070.070.010 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Prepare Product Backlog for Next Release/Sprint |  | Agile | 70 | 10 | AG.16;#228 |  | Bluefield;#Brownfield;#Greenfield
5.070.070.020 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Conduct Release Retrospective |  | Agile | 70 | 20 | AG.05;#225 |  | Bluefield;#Brownfield;#Greenfield
5.070.070.030 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Update the Release and Sprint plan |  | Agile | 70 | 30 | AG.16;#228 |  | Bluefield;#Brownfield;#Greenfield
1..000.000 | Discover | Yes | No | Both | yes | Yes |  |  |  |  | All | Discover |  | Waterfall;#Agile | 0 | 0
| Discover | Yes | No | Template | no | Yes |  |  |  |  | Project Management​ | Strategic Planning
1.070.010.010 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Project Management​ | Create an Innovation Strategy and a High-Level Road Map | Ceate a company specific innovation strategy, and to derive a high-level multi-year road map. Identification of strategic business and IT objectives, including current pain areas. Those objectives need to be clustered to “benefit areas”. For each benefit area, enablers (like SAP S/4HANA, but also other solution or platform components) need to be identified, prioritized, and benchmarked with respect to the industry reference architecture. | Waterfall;#Agile | 10 | 10
1.010.010.010 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Analytics | Define the Analytics Architecture |  | Waterfall;#Agile | 10 | 10
1.070.010.020 | Discover | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Accelerate Your Innovations with the Help of Intelligent Technologies (Optional Task) |  | Waterfall;#Agile | 10 | 20
1.090.010.030 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Security & Authorization | Create a 360-Degree View on Security | Initial security approach and scope identified, including systems that will be supporting it | Waterfall;#Agile | 10 | 30
1.100.020.000 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Solution Design & Build | Application Value and Scoping |  | Waterfall;#Agile | 20 | 0
1.070.010.030 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Project Management​ | Discover the Value of SAP S/4HANA for Your Company |  | Waterfall;#Agile | 10 | 30
1.100.010.040 | Discover | Yes | Yes | Template | yes | Yes |  |  |  |  | Solution Design & Build | Identify the impact of SAP S/4HANA on existing business processes |  | Waterfall;#Agile | 10 | 40
1.070.010.050 | Discover | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Check the Conversion Readiness of SAP ERP |  | Waterfall;#Agile | 10 | 50
1.100.010.060 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Solution Design & Build | Perform a Business Scenario & Solution Mapping |  | Waterfall;#Agile | 10 | 60
1.070.010.070 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Project Management​ | Define the Implementation Strategy |  | Waterfall;#Agile | 10 | 70
1.070.010.080 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Project Management​ | Create a Strategic Road Map & Value Case |  | Waterfall;#Agile | 10 | 80
1.020.030.010 | Discover | Yes | Yes | Template | yes | Yes |  |  |  |  | Architecture | Provide a Trial System from SAP (or use Tenthpin demo system) |  | Waterfall;#Agile | 30 | 10
2.070.020.000 | Prepare | Yes |  | Template | yes | Yes |  |  |  |  | Project Management​ | Project Initiation |  | Waterfall;#Agile | 20 | 0
2.070.020.010 | Prepare | not needed |  | Template | yes | Yes |  |  |  | remove and replace | Project Management​ | Conduct Handover Meeting(s) from Opportunity Phase |  | Waterfall;#Agile | 20 | 10
2.070.020.010 | Prepare | Yes |  | Template | yes | Yes |  |  |  | replace Activate version | Project Management​ | Conduct Handover Meeting(s) from Discover Phase & Team
2.070.020.020 | Prepare | Yes |  | Template | yes | Yes |  |  |  | replace Activate version | Project Management​ | Clarify all SOW assumptions with vendor & SI
2.070.020.030 | Prepare | Yes |  | Template | yes | Yes |  |  |  |  | Project Management​ | Identify Stakeholders, Stakeholders' Requirements and Expectations and Project/deliverable Acceptance Criteria |  | Waterfall;#Agile | 20 | 30
2.070.020.040 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Set Stakeholder Expectations for Agile Project |  | Agile | 20 | 40
1.070.010.050 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Check the Conversion Readiness of SAP ERP |  | Waterfall;#Agile | 10 | 50
1.070.010.050 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Define Scope & Objectives |  | Waterfall;#Agile | 10 | 50
1.070.010.050 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Define Business Process Performance Baseline |  | Waterfall;#Agile | 10 | 50
1.070.010.050 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Model As Is Processes |  | Waterfall;#Agile | 10 | 50
1.070.010.050 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Define Cutover Approach |  | Waterfall;#Agile | 10 | 50
1.070.010.050 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Clarify Custom Code Adoption |  | Waterfall;#Agile | 10 | 50
1.070.010.050 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Clarify Operational Readiness |  | Waterfall;#Agile | 10 | 50
2.070.020.050 | Prepare | Yes |  | Template | yes | Yes |  | Yes |  |  | Project Management​ | Create Project Charter |  | Waterfall;#Agile | 20 | 50
2..000.000 | Prepare- Soft Launch | Yes |  | Template | yes | no |  |  |  |  | All | Prepare- Soft Launch |  | Waterfall;#Agile | 0 | 0
2..000.000 | Prepare- Soft Launch | Yes |  | Template | yes | no |  |  |  |  | All | Prepare- Full Launch
2..000.000 | Prepare- Soft Launch | Yes |  | Template | yes | no |  |  |  |  | Project Management​ | Prepare- Regular Phase Activities
2..000.000 | Prepare- Soft Launch | Yes |  | Template | yes | No |  |  |  |  | All | Team Specific Activities

## Sheet3
Phase | Prepare
Row Labels | Detailed Description
Activate Solution | (blank)
Activation of Best Practices and Test-Activated Processes (New Implementation only) | (blank)
Analysis - Dormant Master Data (supplier, customer, item..) | (blank)
Approval (PREPARE KEY DELIVERABLES)
Assess Workshops readiness | (blank)
Build an overlay of all the plans for the Release | (blank)
Business Process Map | (blank)
Check availability of SAP Solution Manager | (blank)
Check the Conversion Readiness of SAP ERP | (blank)
Clarify all SOW assumptions with vendor & SI | (blank)
Clarify Custom Code Adoption | (blank)
Clarify Operational Readiness | (blank)
Cleanup Unused Code (Optional Task) | (blank)
Communicate & Reinforce Program documentation templates usage | (blank)
Communicate Status and Progress to Project Stakeholders | (blank)
Complete HW Sizing Estimation for Solution landscape | (blank)
Complete the Data Migration Approach and Strategy Document | The purpose of this activity to collect input needed for the Data Migration Approach and Strategy document, in a format suitable for both communication purpose as well as for formal sign-off purpose.​
Conduct Agile Training for the Project Team | (blank)
Conduct Change Management & Training Workshop with Project Manager and all Project Workstream Owners. | (blank)
Conduct Data Audit (Data Health Check) | The purpose of the data audit is to identify the legacy systems that will supply data for the SAP applications and to profile the quality of the legacy data.​
Conduct Handover Meeting(s) from Discover Phase & Team | (blank)
Conduct Handover Meeting(s) from Opportunity Phase | (blank)
Conduct Initial Data Migration Workshop | The purpose of the data migration workshop deliverable is to perform a two-day scoping workshop to explain the SAP data migration approach and to understand the customer’s legacy data systems, business priorities, and technical infrastructure.​
Conduct Key User training | (blank)
Conduct Kick-off Meeting | (blank)
Conduct Knowledge Management Gate | (blank)
Conduct Project Management Review Service | (blank)
Conduct Project Quality Gate | (blank)
Conduct Project Team Enablement prior to Fit-Gap Analysis | (blank)
Conduct SAP Solution Manager training | (blank)
Confirm attendees and send invites | (blank)
Confirm Deployment Start Readiness | (blank)
Confirm Global Core IT Teams for Program Release | (blank)
Confirm Site Assessment Accelerators | (blank)
Confirm Site Assessment Activities | (blank)
Confirm Site Assessment Deliverables | (blank)
Create Budget | (blank)
Create Delta Design and Configuration Requirements Template | (blank)
Create Project Charter | (blank)
Create Project Management Plan | (blank)
Create Project Schedule | (blank)
Create Scope Statement | (blank)
Create WBS | (blank)
Data | (blank)
Data cleansing & Data augmentation | (blank)
Data Cleansing Workshops scheduled | (blank)
Data Definition & Governance | (blank)
Data Migration Approach and Strategy | The purpose of the data migration approach and Strategy deliverable is to capture and communicate the approach and strategy for the legacy data migration. This deliverable is intended to educate the SAP and customer project team members on the SAP data migration framework and methodology used to support the data migration project. In addition, the scope and requirement for data migration should also be determined.​
Data migration strategy presented to local teams | (blank)
Data Migration Workshops scheduled | (blank)
Data Readiness | (blank)
Define and Set Up Agile Project Standards and ALM Tools | (blank)
Define Business Process Performance Baseline | (blank)
Define Cutover Approach | (blank)
Define Project Organization | (blank)
Define Project Standards (e.g. Templates) | (blank)
Define Roles and Responsibilities | (blank)
Define Scope & Objectives | (blank)
Define Solution Deployment Concept | (blank)
Define Solution Landscape Concept | (blank)
Define Technical Architecture | (blank)
Define/review Country Specific Definitions (Language, Unit of meas…  | (blank)
Demonstrate the Business Processes and Pre-defined Options List for SCOPE OPTION | (blank)
Designate data migration/MDM roles | (blank)
Determine Operational Standards | (blank)
Direct and Manage Project Execution | (blank)
Enhance system with additional configuration and test | (blank)
Establish Entry & exit criteria (Define test entry and exit criteria for each… | (blank)
Establish Project Governance | (blank)
Execution, Monitoring, and Controlling of Results | (blank)
F2T WS Scoping: Mapping business needs & initial set of features | (blank)
Finalize Mandatory System Preparation Activities (System Conversion only) | (blank)
Finalize testing templates (test summary report, test log, traceability … | (blank)
Fit-to-Standard System Preparation | (blank)
Fit-to-Standard Workshop Preparation | (blank)
Fit-to-Template Workshops Scoping & Schedule | (blank)
Global template Interface catalogue reviewed | (blank)
High level scope based on BPML (Preliminary BPML L3-L4 selection i… | (blank)
Identify and Resolve milestone conflicts and align dependencies | (blank)
Identify Stakeholders, Stakeholders' Requirements and Expectations and Project/deliverable Acceptance Criteria | (blank)
Import the Best Practice Content | The purpose of this task is to import the SAP Activate Best Practices content either in SAP Signavio or into SAP Solution Manager depending on which tool will support the functional design activities.
Improve Custom Code Quality Measures (Optional Task) | (blank)
Infrastructure and environments | (blank)
Initial Hardware Sizing Proposal | (blank)
Initial profiling of the data (using IDQ) | (blank)
Install or Upgrade SAP Solution Manager | (blank)
Install SAP GUI on Project Team Computers | (blank)
Integration System Governance | (blank)
List of reports currently used (AS IS) in each site | (blank)
Make yourself familiar with Fit-to-Standard | (blank)
Manage Issues, Risks and Changes | (blank)
Mapping Business Needs | (blank)
MDM Basic/Generic Training (standard concepts) | (blank)
Model As Is Processes | (blank)
Monitor and Control Project Activities | (blank)
Obtain Customer Sign-Off for Phase Completion | (blank)
On-board Project Team | (blank)
Organizational Change Management Roadmap | (blank)
Perform Mobilization Training for the Project Team | (blank)
Phase Closure and Sign-Off phase Deliverables | (blank)
Plan Communications | (blank)
Plan Procurement | (blank)
Plan Project | (blank)
Plan Quality | (blank)
Plan Risks | (blank)
Plan Stakeholders Management | (blank)
Prepare and Schedule Workshops | (blank)
Prepare Authorization Roles in the Sandbox Systems for the Project Team | (blank)
Prepare Business Process Map | (blank)
Prepare Data Migration Workshop | The purpose of this task is to make the necessary arrangements for the execution of the workshop.​
Prepare for Kick-off Meeting | (blank)
Prepare Organizational Change Management Roadmap | (blank)
Prepare Scope Document for Workshop | (blank)
Prepare Team Onboarding Document | (blank)
Prepare WS material | (blank)
Present MDM Data Definition & Governance and Data Migration start… | (blank)
Produce F2T workshops Schedule | (blank)
Project Initiation | (blank)
Project Kick-off and On-Boarding | (blank)
Project Plans Review and Validation By Team | (blank)
Project Standards & Infrastructure | (blank)
Project Support Tools and System Setup | (blank)
Project Team Enablement | (blank)
Reconfirmation of Scope for Activation (New Implementation only) | (blank)
Record Customer Selected Options and Finalize Scope Document | (blank)
Review Project Management Plan | (blank)
Review Scope Statement with Customer | (blank)
Schedule MDM Data Definition & Governance and Data Migration Workshops | (blank)
Self-Enable on SAP Process Insights and SAP Signavio | (blank)
Set Stakeholder Expectations for Agile Project | (blank)
Set up Business Process Hierarchy in SAP Solution Manager | (blank)
Set up Integration with other Test Systems | (blank)
Set Up Sandbox | (blank)
Setup and Test Remote Support | (blank)
Setup of Project Logistics and Infrastructure, Including Team Collaboration Environment | (blank)
Setup Project Team Logistics and Infrastructure | (blank)
Support Materials Completed | (blank)
Systems configuration | (blank)
Technical Requirements and Design and Solution Landscape Deployment Plan | (blank)
Test Remote Access and Establish OSS Connection (both GUI and Web Access) | (blank)
Training and templates | (blank)
Transition Preparation | (blank)
Validate and Complete Business Process Map | (blank)
Verify Client/System Strategy (for User Training, UAT, etc.) | (blank)
Verify Cut-Over Strategy for Program Release | (blank)
Verify Defect Management Strategy for Program Release | (blank)
Verify Functional System Requirements | (blank)
Verify Infrastructure Support Strategy for local sites for Program Rel…  | (blank)
Verify Legacy System Discontinuation Strategy for Program Release | (blank)
Verify Release strategy for Program Release | (blank)
Verify System Readiness for Workshops | (blank)
Verify Technical System Requirements (Frontend / Backend) | (blank)
Verify Testing Strategy for Program Release | (blank)
Workshop Participant Enablement | (blank)
Grand Total