## Sheet1
Unique ID | Phase | In Scope | Optional | Template vs Deployment | TMC 2020 | In Activate? | Ferring - Deployment | Ferring - Template | Biontech | Action | Responsible Team/Workstream | Description | Detailed Description | Waterfall / Agile | L3 | L4 | Activate Deliverables / Accelerators | TMC Deliverables / Accelerators | Implementation Type
New | Explore | Yes |  | Both |  | No |  |  |  |  | Project Management​ | Explore- Regular Phase Activities
3.070.010.000 | Explore | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Phase Initiation |  | Waterfall;#Agile | 10 | 0 |  |  | Brownfield;#Greenfield;#Bluefield
3.070.010.010 | Explore | Yes |  | Both | yes | Yes | yes |  |  |  | Project Management​ | Review Deliverables of Explore Phase |  | Waterfall;#Agile | 10 | 10 |  |  | Brownfield;#Greenfield;#Bluefield
3.070.010.020 | Explore | Yes |  | Both | yes | Yes | yes |  |  |  | Project Management​ | Review Acceptance Criteria |  | Waterfall;#Agile | 10 | 20 |  |  | Brownfield;#Greenfield;#Bluefield
3.070.010.030 | Explore | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Review RACI Chart for Explore Phase |  | Waterfall;#Agile | 10 | 30 |  |  | Brownfield;#Greenfield;#Bluefield
3.070.020.000 | Explore | Yes |  | Both | yes | Yes | yes |  |  |  | Project Management​ | Execution, Monitoring and Controlling Results | Set up WS alignment meetings , gap governance meetings | Waterfall;#Agile | 20 | 0 | BOM.131;#274;#PM.41;#317 |  | Brownfield;#Greenfield;#Bluefield
3.070.020.010 | Explore | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Update Project Management Plan |  | Waterfall;#Agile | 20 | 10 |  |  | Brownfield;#Greenfield;#Bluefield
3.070.020.020 | Explore | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Direct and Manage Project Execution |  | Waterfall;#Agile | 20 | 20 | AG.16;#228 |  | Brownfield;#Greenfield;#Bluefield
3.070.020.030 | Explore | Yes | Yes | Both | yes | Yes |  |  |  |  | Project Management​ | Conduct SCRUM Meetings |  | Agile | 20 | 30 | AG.19;#231 |  | Brownfield;#Greenfield;#Bluefield
3.070.020.040 | Explore | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Monitor and Control Project Activities |  | Waterfall;#Agile | 20 | 40 |  |  | Brownfield;#Greenfield;#Bluefield
3.070.020.050 | Explore | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Manage Issues, Risks and Changes |  | Waterfall;#Agile | 20 | 50 | PM.44;#318;#PM.45;#319 |  | Brownfield;#Greenfield;#Bluefield
3.070.020.060 | Explore | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Communicate Status and Progress to Project Stakeholders |  | Waterfall;#Agile | 20 | 60 | PM.41;#317 |  | Brownfield;#Greenfield;#Bluefield
3.070.410.000 | Explore | Yes |  | Both | yes | Yes | yes |  |  |  | Project Management​ | Phase Closure and Sign-Off phase Deliverables |  | Waterfall;#Agile | 410 | 0 |  |  | Brownfield;#Greenfield;#Bluefield
3.070.410.010 | Explore | not needed |  | Both | yes | Yes |  |  |  | remove | Project Management​ | Conduct Knowledge Management Gate |  | Waterfall;#Agile | 410 | 10 | PM.81;#322;#PM.80;#321 |  | Brownfield;#Greenfield;#Bluefield
3.050.320.000 | Explore |  |  | Both | yes | Yes |  |  |  |  | Integration | Integration Design |  | Waterfall;#Agile | 320 | 0 |  |  | Brownfield;#Greenfield;#Bluefield
3.050.320.010 | Explore |  |  | Both | yes | Yes |  |  |  |  | Integration | Define Interface Architecture |  | Waterfall;#Agile | 320 | 10 |  |  | Brownfield;#Greenfield;#Bluefield
3.050.320.020 | Explore |  |  | Both | yes | Yes |  |  |  |  | Integration | Prepare Integration Design |  | Waterfall;#Agile | 320 | 20 |  |  | Brownfield;#Greenfield;#Bluefield
2.060.020.055 | Explore |  |  | Template | yes | no |  | Yes |  | this is too early, move to explore | MDM | Prepare Data Migration Object List with instruction | The purpose of this task is to prepare Data Migration Object List with instruction, pre-requisite​ and plan. | Waterfall;#Agile | 20 | 55 |  | 065.54;#31 | Greenfield
2.060.020.060 | Explore |  |  | Template | yes | no |  |  |  | this is too early, move to explore | MDM | Prepare Data Migration Scope and Requirements Document | The purpose of this task is to prepare the data migration scope and requirements document that captures the overall scope and requirements of the data migration effort.​ | Waterfall;#Agile | 20 | 60 |  |  | Greenfield
2.060.020.070 | Explore |  |  | Template | yes | no |  |  |  | this is too early, move to explore | MDM | Present Data Migration scope and requirements document | The purpose of this task is to present data migration scope and requirements document to customer project team and obtain buy in.​ | Waterfall;#Agile | 20 | 70 |  |  | Greenfield
2.060.020.080 | Explore |  |  | Template | yes | no |  |  |  | this is too early, move to explore | MDM | Conduct Organizational Assessment for Data Migration | The purpose of this task is to assess customer organization for the demands of data migration process. The outcome of this task is documented current state of the organization and required target state.​ | Waterfall;#Agile | 20 | 80 |  |  | Greenfield
2.060.020.090 | Explore |  |  | Template | yes | no |  | Yes |  | this is too early, move to explore | MDM | Conduct Infrastructure Assessment for Data Migration/Data | The purpose of this task is to assess customer infrastructure for the needs of the data migration process. As a result the project team learns about available tools and identifies any gaps/requirements to acquire tools to support the migration process.​ | Waterfall;#Agile | 20 | 90 |  |  | Greenfield
2.060.020.100 | Explore |  |  | Template | yes | no |  | Yes |  | this is too early, move to explore | MDM | Conduct Risk Assessment for Data Migration and Prepare Mitigation Plan | The purpose of this task is to assess risk for the data migration activities. The risk assessment focuses on organization, technical risk, data quality risk and other risks that may impact the data migration activities. During this task the team prepares mitigation strategies for the individual risk items in the risk register.​ | Waterfall;#Agile | 20 | 100 |  |  | Greenfield
2.060.020.120 | Explore |  |  | Template | yes | no |  | Yes |  | this is too early, move to explore | MDM | Discuss Data Requirements and Format for Later Upload into the Solution for | The purpose of this task is to ensure a common understanding of the master data required for upload into the solution, what format and when it needs to be available for upload.​ | Waterfall;#Agile | 20 | 120
2.060.020.130 | Explore |  |  | Template | yes | no |  | Yes |  | this is too early, move to explore | MDM | Define the Data Migration Architecture | The purpose of this task is to prepare Data Migration Architecture for the needs of the data migration process which fits to company overall Architecture. | Waterfall;#Agile | 20 | 130 |  |  | Greenfield
New | Explore | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Data Definition & Governance
New | Explore | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Fit-to-Template Analysis
New | Explore | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Participate in E2E Fit-to-Template Workshops
3.090.170.000 | Explore | Yes |  | Template | yes | Yes |  |  |  |  | Security & Authorization | Security Design |  | Waterfall;#Agile | 170 | 0 |  |  | Brownfield;#Greenfield;#Bluefield
3.090.170.010 | Explore | Yes |  | Template | yes | no |  |  |  | rename | Security & Authorization | SAP SEC Standards and Design document | Template roles are defined and shared with Teams , Concept of Business & System user Role identified | Waterfall;#Agile | 170 | 10 |  |  | Bluefield;#Brownfield;#Greenfield
Security Infrastructure is defined, derived roles concept has been developed, to be mapped to localisation requirements
3.090.350.050 | Explore | Yes |  | Both | yes | No |  | Yes |  |  | Security & Authorization | Set up Role assignment / Authorizations / Test Users in DEV |  | Waterfall;#Agile | 350 | 50 |  |  | Brownfield;#Greenfield;#Bluefield
NEW | Explore | Yes |  | Template | no | No |  | Yes |  |  | Security & Authorization | Define User Management Process for Project systems | Establish user management process for DEV, Q & Prod systems
NEW | Explore | Yes |  | Deployment | no | No | Yes |  |  |  | Security & Authorization | Assessment of Local Roles requirements by Process Area
NEW | Explore | Yes |  | Template | no | no | Yes |  |  |  | Security & Authorization | Creation of plan & effort for GRC: Access Control implementation | , including any links to HR systems such as Workday and Access Control ruleset
New | Explore | Yes |  | Both | no | no | yes |  |  |  | Security & Authorization | Global Team access definition - SAP Development (DEV & QAS )
3.100.220.020 | Explore | Yes |  | Both | yes | No |  |  |  | Generic agile | Solution Design & Build | Define User Stories and Update Product Backlog |  | Agile | 220 | 20
3.100.220.030 | Explore | Yes |  | Both | yes | No |  |  |  | Generic agile | Solution Design & Build | Develop Stories Board |  | Agile | 220 | 30
3.100.120.000 | Explore | Yes |  | Both | yes | Yes |  | Yes |  |  | Solution Design & Build | Fit-to-Standard Workshops and Documentation |  | Waterfall;#Agile | 120 | 0 |  |  | Brownfield;#Greenfield;#Bluefield
3.100.120.010 | Explore | Yes |  | Both | yes | Yes |  | Yes |  |  | Solution Design & Build | Fit-to-Standard Workshops Execution |  | Waterfall;#Agile | 120 | 10 |  |  | Brownfield;#Greenfield;#Bluefield
3.100.120.011 | Explore | Yes |  | Both | no | no | Yes | Yes |  |  | Solution Design & Build | Fit to Standard Workshops A | By L3 Process or other logical grouping
3.100.120.012 | Explore | Yes |  | Both | no | no | Yes | Yes |  |  | Solution Design & Build | Workshops B Preparation (support materials and updates to system prototype)
3.100.120.012 | Explore | Yes |  | Both | no | no | Yes | Yes |  |  | Solution Design & Build | Fit to Standard Workshops B | By L3 Process or other logical grouping
3.100.120.020 | Explore | Yes |  | Both | yes | Yes | Yes | Yes |  |  | Solution Design & Build | Fit-to-Standard Workshop Documentation |  | Waterfall;#Agile | 120 | 20 |  |  | Brownfield;#Greenfield;#Bluefield
3.100.120.020 | Explore | Yes |  | Both | no | No | Yes | Yes |  |  | Solution Design & Build | Document requirements in the Templates provided
3.100.120.021 | Explore | Yes |  | Both | no | No | Yes | Yes |  |  | Solution Design & Build | Collect all business requirements
3.100.120.022 | Explore | Yes |  | Both | no | No | Yes | Yes |  |  | Solution Design & Build | Update Requirements tracker
5..000.000 | Deploy |  |  | Both | yes | Yes |  |  |  |  | All | Deploy |  | Waterfall;#Agile | 0 | 0
5.070.010.000 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Phase Initiation |  | Waterfall;#Agile | 10 | 0 | PM.01;#290 |  | Brownfield;#Greenfield;#Bluefield
5.070.010.010 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Allocate Resources and Update Project Schedule |  | Waterfall;#Agile | 10 | 10 |  |  | Brownfield;#Greenfield;#Bluefield
5.070.010.020 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Perform Kickoff Meeting |  | Waterfall;#Agile | 10 | 20 | PM.13;#295 |  | Brownfield;#Greenfield;#Bluefield
5.070.020.000 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Execution, Monitoring and Controlling Results |  | Waterfall;#Agile | 20 | 0 | BOM.131;#274;#PM.41;#317 |  | Brownfield;#Greenfield;#Bluefield
5.070.020.010 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Update Project Management Plan |  | Waterfall;#Agile | 20 | 10 |  |  | Brownfield;#Greenfield;#Bluefield
5.070.020.020 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Direct and Manage Project Execution |  | Waterfall;#Agile | 20 | 20 |  |  | Brownfield;#Greenfield;#Bluefield
5.070.020.030 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Monitor and Control Project Activities |  | Waterfall;#Agile | 20 | 30 |  |  | Brownfield;#Greenfield;#Bluefield
5.070.020.040 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Manage Issues, Risks and Changes |  | Waterfall;#Agile | 20 | 40 | PM.44;#318;#PM.45;#319 |  | Brownfield;#Greenfield;#Bluefield
5.070.020.050 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Communicate Status and Progress to Project Stakeholders |  | Waterfall;#Agile | 20 | 50 | PM.41;#317 |  | Brownfield;#Greenfield;#Bluefield
5.070.070.000 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Release Closing |  | Agile | 70 | 0 |  |  | Bluefield;#Brownfield;#Greenfield
5.070.070.010 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Prepare Product Backlog for Next Release/Sprint |  | Agile | 70 | 10 | AG.16;#228 |  | Bluefield;#Brownfield;#Greenfield
5.070.070.020 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Conduct Release Retrospective |  | Agile | 70 | 20 | AG.05;#225 |  | Bluefield;#Brownfield;#Greenfield
5.070.070.030 | Deploy | Yes |  | Deployment | yes | Yes |  |  |  |  | Project Management​ | Update the Release and Sprint plan |  | Agile | 70 | 30 | AG.16;#228 |  | Bluefield;#Brownfield;#Greenfield
New | Deploy | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Data Readiness
New | Deploy | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Conduct Data Quality Readiness Check
New | Deploy | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Obtain Production Data Load Sign-o
New | Deploy | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Perform Cutover Activities, Final Production Data Load
New | Deploy | Yes |  | Deployment | no | no | yes |  |  |  | Security & Authorization | Mass user creation & role assignment
New | Deploy | Yes |  | Deployment | no | no | yes |  |  |  | Security & Authorization | Authorisation issues support
New | Deploy | Yes |  | Deployment | no | no | yes |  |  |  | Security & Authorization | Hypercare roles for IT definition (Creation of roles for elevated access)
New | Deploy | Yes |  | Deployment | no | no | yes |  |  |  | Security & Authorization | Authorisation issues support
New | Deploy | Yes |  | Deployment | no | no | yes |  |  |  | Solution Design & Build | Global SOPs updated and approved
New | Deploy | Yes |  | Deployment | no | no | yes |  |  |  | Solution Design & Build | Local SOPs updated and approved
New | Deploy | Yes |  | Deployment | no | no | yes |  |  |  | Solution Design & Build | Support end-user training
New | Deploy | Yes |  | Deployment | no | no | yes |  |  |  | Solution Design & Build | Support Cutover plan activities
New | Deploy | Yes |  | Deployment | no | no | yes |  |  | This is Deploy in Activate , Run in Ferring | Solution Design & Build | Production Support and Go Live - Hypercare
New | Deploy | Yes |  | Deployment | no | no | yes |  |  | This is Deploy in Activate , Run in Ferring | Solution Design & Build | Attend Hypercare sessions
New | Deploy | Yes |  | Deployment | no | Yes | yes |  |  | This is Deploy in Activate , Run in Ferring | Solution Design & Build | Resolve Functional Issues
New | Deploy | Yes |  | Deployment | no | Yes | yes |  |  | This is Deploy in Activate , Run in Ferring | Solution Design & Build | Resolve Technical Issues
New | Deploy | Yes |  | Deployment | no | Yes | yes |  |  | This is Deploy in Activate , Run in Ferring | Solution Design & Build | Handover and KT to support organisation
1..000.000 | Discover | Yes | No | Both | yes | Yes |  |  |  |  | All | Discover |  | Waterfall;#Agile | 0 | 0
| Discover | Yes | No | Template | no | Yes |  |  |  |  | Project Management​ | Strategic Planning
1.070.010.010 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Project Management​ | Create an Innovation Strategy and a High-Level Road Map | Ceate a company specific innovation strategy, and to derive a high-level multi-year road map. Identification of strategic business and IT objectives, including current pain areas. Those objectives need to be clustered to “benefit areas”. For each benefit area, enablers (like SAP S/4HANA, but also other solution or platform components) need to be identified, prioritized, and benchmarked with respect to the industry reference architecture. | Waterfall;#Agile | 10 | 10
1.010.010.010 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Analytics | Define the Analytics Architecture |  | Waterfall;#Agile | 10 | 10
1.070.010.020 | Discover | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Accelerate Your Innovations with the Help of Intelligent Technologies (Optional Task) |  | Waterfall;#Agile | 10 | 20
1.090.010.030 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Security & Authorization | Create a 360-Degree View on Security | Initial security approach and scope identified, including systems that will be supporting it | Waterfall;#Agile | 10 | 30
1.100.020.000 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Solution Design & Build | Application Value and Scoping |  | Waterfall;#Agile | 20 | 0
1.070.010.030 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Project Management​ | Discover the Value of SAP S/4HANA for Your Company |  | Waterfall;#Agile | 10 | 30
1.100.010.040 | Discover | Yes | Yes | Template | yes | Yes |  |  |  |  | Solution Design & Build | Identify the impact of SAP S/4HANA on existing business processes |  | Waterfall;#Agile | 10 | 40
1.070.010.050 | Discover | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Check the Conversion Readiness of SAP ERP |  | Waterfall;#Agile | 10 | 50
1.100.010.060 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Solution Design & Build | Perform a Business Scenario & Solution Mapping |  | Waterfall;#Agile | 10 | 60
1.070.010.070 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Project Management​ | Define the Implementation Strategy |  | Waterfall;#Agile | 10 | 70
1.070.010.080 | Discover | Yes | No | Template | yes | Yes |  |  |  |  | Project Management​ | Create a Strategic Road Map & Value Case |  | Waterfall;#Agile | 10 | 80
1.020.030.010 | Discover | Yes | Yes | Template | yes | Yes |  |  |  |  | Architecture | Provide a Trial System from SAP (or use Tenthpin demo system) |  | Waterfall;#Agile | 30 | 10
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Site Assessment (Quick Scan) Output Review
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Identify integration topics by reviewing defined scope
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Assess Complexity and Size of the site based on BPML and WRICEF s
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Estimate efforts for assessed scope (BPML+WRICEF)
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Challenge round for foreseen high level scope
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Identify resource and skills hot spots, assess capacity for following … 
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Socialize/share Capacity Assessment
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Define Teams structure and model to accomplish the Release
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Identify local budget impacts and backfills
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Template Governance (initial assessment)
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Define and Align Deployment Strategy
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Review the Discovery Phase output summary final presentation
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Reconfirm L1/L2 timelines for this Release
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Confirm L1/L2 Template plan feasibility for the current Release
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Solution Design & Build | Site Assessment- QuickScan
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Solution Design & Build | Quickscan answers review by PO and CoE SA
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Solution Design & Build | Clarification calls (optional)
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Solution Design & Build | List of hot spots per site identified (complexity or deviations from template
New | Discover | Yes |  | Deployment | no | no | yes |  |  |  | Solution Design & Build | QuickScan questionnaire template improvements
2.100.010.060 | Discover | Yes |  | Template | yes | Yes |  |  |  | In Discover Phase in Activate but might be too early , move to Architecture | Architecture | Define the UX / UI strategy |  | Waterfall;#Agile | 10 | 60
2.070.020.000 | Prepare | Yes |  | Template | yes | Yes |  |  |  |  | Project Management​ | Project Initiation |  | Waterfall;#Agile | 20 | 0
2.070.020.010 | Prepare | not needed |  | Template | yes | Yes |  |  |  | remove and replace | Project Management​ | Conduct Handover Meeting(s) from Opportunity Phase |  | Waterfall;#Agile | 20 | 10
2.070.020.010 | Prepare | Yes |  | Template | yes | Yes |  |  |  | replace Activate version | Project Management​ | Conduct Handover Meeting(s) from Discover Phase & Team
2.070.020.020 | Prepare | Yes |  | Template | yes | Yes |  |  |  | replace Activate version | Project Management​ | Clarify all SOW assumptions with vendor & SI
2.070.020.030 | Prepare | Yes |  | Template | yes | Yes |  |  |  |  | Project Management​ | Identify Stakeholders, Stakeholders' Requirements and Expectations and Project/deliverable Acceptance Criteria |  | Waterfall;#Agile | 20 | 30
2.070.020.040 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Set Stakeholder Expectations for Agile Project |  | Agile | 20 | 40
1.070.010.050 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Check the Conversion Readiness of SAP ERP |  | Waterfall;#Agile | 10 | 50
1.070.010.050 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Define Scope & Objectives |  | Waterfall;#Agile | 10 | 50
1.070.010.050 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Define Business Process Performance Baseline |  | Waterfall;#Agile | 10 | 50
1.070.010.050 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Model As Is Processes |  | Waterfall;#Agile | 10 | 50
1.070.010.050 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Define Cutover Approach |  | Waterfall;#Agile | 10 | 50
1.070.010.050 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Clarify Custom Code Adoption |  | Waterfall;#Agile | 10 | 50
1.070.010.050 | Prepare | Yes | Yes | Template | yes | Yes |  |  |  |  | Project Management​ | Clarify Operational Readiness |  | Waterfall;#Agile | 10 | 50
2.070.020.050 | Prepare | Yes |  | Template | yes | Yes |  | Yes |  |  | Project Management​ | Create Project Charter |  | Waterfall;#Agile | 20 | 50
2.070.020.060 | Prepare | Yes |  | Template | yes | Yes |  |  |  |  | Project Management​ | Create Project Management Plan |  | Waterfall;#Agile | 20 | 60
2.070.030.000 | Prepare | Yes |  | Template | yes | Yes |  | Yes |  |  | Project Management​ | Establish Project Governance |  | Waterfall;#Agile | 30 | 0
2.070.030.010 | Prepare | Yes |  | Template | yes | Yes |  | Yes |  |  | Project Management​ | Define Roles and Responsibilities |  | Waterfall;#Agile | 30 | 10
2.070.030.020 | Prepare | Yes |  | Template | yes | Yes |  | Yes |  |  | Project Management​ | Define Project Organization |  | Waterfall;#Agile | 30 | 20
2.070.030.030 | Prepare | Yes |  | Template | yes | Yes |  |  |  |  | Project Management​ | Review Project Management Plan |  | Waterfall;#Agile | 30 | 30
2.070.070.000 | Prepare | Yes |  | Both | yes | Yes |  | Yes |  |  | Project Management​ | Project Standards & Infrastructure |  | Waterfall;#Agile | 70 | 0
2.070.070.010 | Prepare | Yes |  | Template | yes | Yes |  | Yes |  |  | Project Management​ | Define Project Standards (e.g. Templates) |  | Waterfall;#Agile | 70 | 10
2.100.110.070 | Prepare |  |  | Template | yes | No |  | Yes |  | Move to PM | Project Management​ | Create Delta Design and Configuration Requirements Template |  | Waterfall;#Agile | 110 | 70
2.070.070.020 | Prepare | Yes |  | Template | yes | Yes |  | Yes |  |  | Project Management​ | Determine Operational Standards |  | Waterfall;#Agile | 70 | 20
2.070.070.030 | Prepare | Yes |  | Template | yes | Yes |  | Yes |  |  | Project Management​ | Define and Set Up Agile Project Standards and ALM Tools |  | Agile | 70 | 30
2.070.070.040 | Prepare | Yes |  | Both | yes | Yes | Yes | Yes |  |  | Project Management​ | Check availability of SAP Solution Manager |  | Waterfall;#Agile | 70 | 40
2.070.070.050 | Prepare | Yes |  | Both | yes | Yes |  | Yes |  |  | Project Management​ | Setup Project Team Logistics and Infrastructure |  | Waterfall;#Agile | 70 | 50
2.070.070.060 | Prepare | Yes |  | Both | yes | Yes |  | Yes |  |  | Project Management​ | Setup and Test Remote Support |  | Waterfall;#Agile | 70 | 60
2.070.040.000 | Prepare |  |  | Both | yes | Yes |  |  |  |  | Project Management​ | Plan Project |  | Waterfall;#Agile | 40 | 0
2.070.040.010 | Prepare |  |  | Both | yes | Yes |  |  |  |  | Project Management​ | Create Scope Statement |  | Waterfall;#Agile | 40 | 10
2.070.040.020 | Prepare |  |  | Both | yes | Yes |  |  |  |  | Project Management​ | Create WBS |  | Waterfall;#Agile | 40 | 20
2.070.040.030 | Prepare |  |  | Both | yes | Yes |  |  |  |  | Project Management​ | Create Project Schedule |  | Waterfall;#Agile | 40 | 30
2.070.040.040 | Prepare |  |  | Both | yes | Yes |  |  |  | remove- This can not be "created" that late- this should be Discover or before | Project Management​ | Create Budget |  | Waterfall;#Agile | 40 | 40
2.070.040.050 | Prepare |  |  | Both | yes | Yes |  |  |  |  | Project Management​ | Plan Quality |  | Waterfall;#Agile | 40 | 50
2.070.040.060 | Prepare |  |  | Both | yes | Yes |  |  |  |  | Project Management​ | Plan Communications |  | Waterfall;#Agile | 40 | 60
2.070.040.070 | Prepare |  |  | Both | yes | Yes |  |  |  |  | Project Management​ | Plan Risks |  | Waterfall;#Agile | 40 | 70
2.070.040.080 | Prepare |  |  | Both | yes | Yes |  |  |  |  | Project Management​ | Plan Procurement |  | Waterfall;#Agile | 40 | 80
2.070.040.090 | Prepare |  |  | Both | yes | Yes |  |  |  |  | Project Management​ | Plan Stakeholders Management |  | Waterfall;#Agile | 40 | 90
2.070.050.000 | Prepare | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Project Kick-off and On-Boarding |  | Waterfall;#Agile | 50 | 0
2.070.050.010 | Prepare | Yes |  | Both | yes | Yes |  | Yes |  |  | Project Management​ | Prepare for Kick-off Meeting |  | Waterfall;#Agile | 50 | 10
2.070.050.020 | Prepare | Yes |  | Both | yes | Yes |  | Yes |  |  | Project Management​ | Conduct Kick-off Meeting |  | Waterfall;#Agile | 50 | 20
2.070.050.030 | Prepare | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Prepare Team Onboarding Document |  | Waterfall;#Agile | 50 | 30
2.070.050.040 | Prepare | Yes |  | Both | yes | Yes |  | Yes |  |  | Project Management​ | On-board Project Team |  | Waterfall;#Agile | 50 | 40
2.070.060.000 | Prepare | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Project Team Enablement |  | Waterfall;#Agile | 60 | 0
2.070.060.030 | Prepare | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Perform Mobilization Training for the Project Team |  | Waterfall;#Agile | 60 | 30
2.070.060.040 | Prepare |  |  | Both | yes | Yes |  |  |  |  | Project Management​ | Conduct Project Team Enablement prior to Fit-Gap Analysis |  | Waterfall;#Agile | 60 | 40
2.070.080.000 | Prepare | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Execution, Monitoring, and Controlling of Results |  | Waterfall;#Agile | 80 | 0
2.070.080.020 | Prepare | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Monitor and Control Project Activities |  | Waterfall;#Agile | 80 | 20
2.070.080.030 | Prepare | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Manage Issues, Risks and Changes |  | Waterfall;#Agile | 80 | 30
2.070.080.040 | Prepare | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Communicate Status and progress to Project Stakeholders |  | Waterfall;#Agile | 80 | 40
2.070.090.010 | Prepare | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Direct and Manage Project Execution |  | Waterfall;#Agile | 90 | 10
2.070.230.000 | Prepare | Yes |  | Both | yes | Yes |  |  |  |  | Project Management​ | Phase Closure and Sign-Off phase Deliverables |  | Waterfall;#Agile | 230 | 0
2.070.230.010 | Prepare | not needed |  | Both | yes | Yes |  |  |  | Remove | Project Management​ | Conduct Knowledge Management Gate |  | Waterfall;#Agile | 230 | 10
2.070.230.020 | Prepare | Yes |  | Both | yes | Yes | Yes | Yes |  |  | Project Management​ | Conduct Project Quality Gate |  | Waterfall;#Agile | 230 | 20
2.070.230.030 | Prepare | not needed |  | Both | yes | Yes |  |  |  | Remove | Project Management​ | Conduct Project Management Review Service |  | Waterfall;#Agile | 230 | 30
2.070.230.040 | Prepare |  |  | Both | yes | Yes |  |  |  |  | Project Management​ | Obtain Customer Sign-Off for Phase Completion |  | Waterfall;#Agile | 230 | 40
2.040.060.010 | Prepare |  |  | Both | yes | Yes |  |  |  | with Change Management & Training? | Change Management & Training | Conduct Agile Training for the Project Team |  | Waterfall;#Agile | 60 | 10
2.040.060.020 | Prepare |  |  | Both | yes | Yes |  |  |  | with Change Management & Training? | Change Management & Training | Conduct SAP Solution Manager training |  | Waterfall;#Agile | 60 | 20
2.040.060.050 | Prepare |  |  | Both | yes | Yes |  |  |  | In Prepare & Realize in Activate as done in instalments | Change Management & Training | Conduct Key User training |  | Waterfall;#Agile | 60 | 50
2.040.090.000 | Prepare |  |  | Both | yes | Yes |  | Yes |  |  | Change Management & Training | Organizational Change Management Roadmap |  | Waterfall;#Agile | 90 | 0
2.040.090.010 | Prepare |  |  | Both | yes | Yes |  | Yes |  |  | Change Management & Training | Prepare Organizational Change Management Roadmap |  | Waterfall;#Agile | 90 | 10
2.040.090.020 | Prepare |  |  | Both | yes | Yes |  |  |  |  | Change Management & Training | Conduct Change Management & Training Workshop with Project Manager and all Project Workstream Owners. |  | Waterfall;#Agile | 90 | 20
New | Prepare |  |  | Both | no | Yes |  |  |  |  | Project Management​ | Self-Enable on SAP Process Insights and SAP Signavio
2.100.110.000 | Prepare |  |  | Both | yes | No |  |  |  | Replace with Signavio steps ? | Solution Design & Build | Business Process Map |  | Waterfall;#Agile | 110 | 0
2.100.110.010 | Prepare |  |  | Both | yes | No |  |  |  | Replace with Signavio steps ? | Solution Design & Build | Prepare Business Process Map |  | Waterfall;#Agile | 110 | 10
2.100.110.020 | Prepare |  |  | Both | yes | No |  |  |  | in workshop prep? | Solution Design & Build | Prepare Scope Document for Workshop |  | Waterfall;#Agile | 110 | 20
2.100.110.040 | Prepare |  |  | Both | yes | No |  |  |  | in workshop prep? | Solution Design & Build | Mapping Business Needs |  | Waterfall;#Agile | 110 | 40
2.100.110.050 | Prepare |  |  | Both | yes | No |  |  |  | in workshop prep? | Solution Design & Build | Record Customer Selected Options and Finalize Scope Document |  | Waterfall;#Agile | 110 | 50
2.100.110.060 | Prepare |  |  | Both | yes | No |  |  |  | in workshop prep? | Solution Design & Build | Review Scope Statement with Customer |  | Waterfall;#Agile | 110 | 60
2.100.110.080 | Prepare |  |  | Both | yes | No |  |  |  | needed? | Solution Design & Build | Validate and Complete Business Process Map |  | Waterfall;#Agile | 110 | 80
3.100.100.000 | Prepare | Yes |  | Both | yes | Yes |  |  |  | in Prepare for TMC/ Explore in Activate | Solution Design & Build | Fit-to-Standard Workshop Preparation |  | Waterfall;#Agile | 100 | 0
3.100.100.010 | Prepare | Yes |  | Both | yes | Yes |  |  |  | in Prepare for TMC/ Explore in Activate | Solution Design & Build | Make yourself familiar with Fit-to-Standard |  | Waterfall;#Agile | 100 | 10
3.100.100.020 | Prepare | Yes |  | Both | yes | Yes |  |  |  | in Prepare for TMC/ Explore in Activate | Solution Design & Build | Prepare and Schedule Workshops |  | Waterfall;#Agile | 100 | 20
New | Prepare | Yes |  | Both | no | no | Yes | Yes |  | in Prepare for TMC/ Explore in Activate | Solution Design & Build | Fit-to-Template Workshops Scoping & Schedule
New | Prepare | Yes |  | Both | no | no | Yes | Yes |  | in Prepare for TMC/ Explore in Activate | Solution Design & Build | High level scope based on BPML (Preliminary BPML L3-L4 selection i…
New | Prepare | Yes |  | Both | no | no | Yes | Yes |  | in Prepare for TMC/ Explore in Activate | Solution Design & Build | F2T WS Scoping: Mapping business needs & initial set of features
New | Prepare | Yes |  | Both | no | no | Yes | Yes |  | in Prepare for TMC/ Explore in Activate | Solution Design & Build | Produce F2T workshops Schedule
New | Prepare | Yes |  | Both | no | No | Yes | Yes |  |  | Solution Design & Build | Prepare WS material
3.100.090.010 | Prepare |  |  | Both | yes | No |  |  |  | same with workshop ? | Solution Design & Build | Demonstrate the Business Processes and Pre-defined Options List for SCOPE OPTION |  | Waterfall;#Agile | 90 | 10
3.100.100.030 | Prepare | Yes |  | Both | yes | Yes |  |  |  | in Prepare for TMC/ Explore in Activate | Solution Design & Build | Workshop Participant Enablement |  | Waterfall;#Agile | 100 | 30
3.100.100.030 | Prepare | Yes |  | Both | no | No |  |  |  |  | Solution Design & Build | Confirm attendees and send invites
2.100.140.000 | Prepare | Yes |  | Both | yes | Yes |  |  |  |  | Solution Design & Build | Activate Solution |  | Waterfall;#Agile | 140 | 0
2.100.140.010 | Prepare | Yes |  | Both | yes | Yes |  |  |  |  | Solution Design & Build | Finalize Mandatory System Preparation Activities (System Conversion only) |  | Waterfall;#Agile | 140 | 10
2.100.140.020 | Prepare | Yes |  | Both | yes | Yes |  |  |  |  | Solution Design & Build | Reconfirmation of Scope for Activation (New Implementation only) |  | Waterfall;#Agile | 140 | 20
2.100.140.030 | Prepare | Yes |  | Both | yes | Yes |  |  |  |  | Solution Design & Build | Activation of Best Practices and Test-Activated Processes (New Implementation only) |  | Waterfall;#Agile | 140 | 30
2.100.140.040 | Prepare | Yes | Yes | Both | yes | Yes |  |  |  |  | Solution Design & Build | Set up Integration with other Test Systems |  | Waterfall;#Agile | 140 | 40
3.100.110.000 | Prepare | Yes |  | Both | yes | Yes |  |  |  | in Prepare for TMC/ Explore in Activate | Solution Design & Build | Fit-to-Standard System Preparation |  | Waterfall;#Agile | 110 | 0
3.100.110.020 | Prepare | Yes |  | Both | yes | Yes |  |  |  | in Prepare for TMC/ Explore in Activate | Solution Design & Build | Enhance system with additional configuration and test |  | Waterfall;#Agile | 110 | 20
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Solution Design & Build | Global template Interface catalogue reviewed
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Solution Design & Build | List of reports currently used (AS IS) in each site
2.100.010.000 | Prepare | Yes | Yes | Both | yes | Yes |  |  |  |  | Solution Design & Build | Transition Preparation |  | Waterfall;#Agile | 10 | 0
2.100.010.020 | Prepare | Yes | Yes | Both | yes | Yes |  |  |  |  | Solution Design & Build | Cleanup Unused Code (Optional Task) |  | Waterfall;#Agile | 10 | 20
2.100.010.030 | Prepare | Yes | Yes | Both | yes | Yes |  |  |  |  | Solution Design & Build | Improve Custom Code Quality Measures (Optional Task) |  | Waterfall;#Agile | 10 | 30
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Confirm Deployment Start Readiness
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Confirm Global Core IT Teams for Program Release
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Confirm Site Assessment Accelerators
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Confirm Site Assessment Deliverables
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Confirm Site Assessment Activities
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Approval (PREPARE KEY DELIVERABLES)
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Verify Testing Strategy for Program Release
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Verify Defect Management Strategy for Program Release
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Verify Client/System Strategy (for User Training, UAT, etc.)
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Verify Cut-Over Strategy for Program Release
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Verify Infrastructure Support Strategy for local sites for Program Rel… 
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Verify Release strategy for Program Release
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Project Management​ | Verify Legacy System Discontinuation Strategy for Program Release
New | Prepare |  |  | Deployment | no | no | yes |  |  | Why is it here? Explore ? | Project Management​ | Integration System Governance
New | Prepare |  |  | Deployment | no | no | yes |  |  | Why is it here? Explore ? | Project Management​ | Define/review Country Specific Definitions (Language, Unit of meas… 
New | Prepare | Yes |  | Both | no | yes |  |  |  |  | Architecture | Define Technical Architecture
2.020.170.000 | Prepare | Yes |  | Both | yes | no |  |  |  |  | Architecture | Technical Requirements and Design and Solution Landscape Deployment Plan |  | Waterfall;#Agile | 170 | 0
2.020.170.010 | Prepare | Yes |  | Both | yes | no |  | Yes |  |  | Architecture | Define Solution Landscape Concept |  | Waterfall;#Agile | 170 | 10
2.020.170.020 | Prepare | Yes |  | Both | yes | no |  | Yes |  |  | Architecture | Define Solution Deployment Concept |  | Waterfall;#Agile | 170 | 20
2.020.190.000 | Prepare | Yes |  | Both | yes | no |  | Yes |  |  | Architecture | Initial Hardware Sizing Proposal |  | Waterfall;#Agile | 190 | 0
2.020.190.010 | Prepare | Yes |  | Both | yes | no |  | Yes |  |  | Architecture | Complete HW Sizing Estimation for Solution landscape |  | Waterfall;#Agile | 190 | 10
2.020.200.000 | Prepare | Yes |  | Both | yes | Yes |  | Yes |  |  | Architecture | Project Support Tools and System Setup |  | Waterfall;#Agile | 200 | 0
2.020.200.010 | Prepare | Yes |  | Both | yes | no |  | Yes |  |  | Architecture | Verify Technical System Requirements (Frontend / Backend) |  | Waterfall;#Agile | 200 | 10
2.020.200.020 | Prepare | Yes |  | Both | yes | no |  |  |  |  | Architecture | Verify Functional System Requirements |  | Waterfall;#Agile | 200 | 20
2.020.200.030 | Prepare | Yes |  | Both | yes | no |  | Yes |  | Extend this to all Tools & change ownership to PM | Architecture | Check Availability of SAP Solution Manager |  | Waterfall;#Agile | 200 | 30
2.020.200.040 | Prepare | Yes |  | Both | yes | no |  | Yes |  |  | Architecture | Install or Upgrade SAP Solution Manager |  | Waterfall;#Agile | 200 | 40
2.020.200.050 | Prepare |  |  | Both | yes | no |  |  |  | This cant not be architecture | Project Management​ | Set up Business Process Hierarchy in SAP Solution Manager |  | Waterfall;#Agile | 200 | 50
New | Prepare | Yes |  | Both | no | Yes |  |  |  |  | Architecture | Import the Best Practice Content | The purpose of this task is to import the SAP Activate Best Practices content either in SAP Signavio or into SAP Solution Manager depending on which tool will support the functional design activities.
2.020.200.060 | Prepare | Yes |  | Both | yes | no |  |  |  |  | Architecture | Setup of Project Logistics and Infrastructure, Including Team Collaboration Environment |  | Waterfall;#Agile | 200 | 60
2.020.200.070 | Prepare | Yes |  | Both | yes | no |  | Yes |  |  | Architecture | Install SAP GUI on Project Team Computers |  | Waterfall;#Agile | 200 | 70
2.020.200.080 | Prepare | Yes |  | Both | yes | no |  |  |  |  | Architecture | Test Remote Access and Establish OSS Connection (both GUI and Web Access) |  | Waterfall;#Agile | 200 | 80
2.020.220.010 | Prepare | Yes |  | Both | yes | Yes |  | Yes |  | consolidated into one item | Architecture | Set Up Sandbox |  | Waterfall;#Agile | 220 | 10
2.090.200.090 | Prepare | Yes |  | Both | yes | No |  | Yes |  | Change it to SBX, not Dev | Security & Authorization | Prepare Authorization Roles in the Sandbox Systems for the Project Team |  | Waterfall;#Agile | 200 | 90
2.060.020.020 | Prepare |  |  | Template | yes | Yes |  | Yes |  |  | MDM | Data Migration Approach and Strategy | The purpose of the data migration approach and Strategy deliverable is to capture and communicate the approach and strategy for the legacy data migration. This deliverable is intended to educate the SAP and customer project team members on the SAP data migration framework and methodology used to support the data migration project. In addition, the scope and requirement for data migration should also be determined.​ | Waterfall;#Agile | 20 | 20
2.060.020.030 | Prepare |  |  | Both | yes | No |  |  |  |  | MDM | Prepare Data Migration Workshop | The purpose of this task is to make the necessary arrangements for the execution of the workshop.​ | Waterfall;#Agile | 20 | 30
2.060.020.040 | Prepare |  |  | Both | yes | No |  |  |  |  | MDM | Conduct Initial Data Migration Workshop | The purpose of the data migration workshop deliverable is to perform a two-day scoping workshop to explain the SAP data migration approach and to understand the customer’s legacy data systems, business priorities, and technical infrastructure.​ | Waterfall;#Agile | 20 | 40
2.060.020.050 | Prepare |  |  | Both | yes | Yes |  |  |  | In Explore in Activate | MDM | Conduct Data Audit (Data Health Check) | The purpose of the data audit is to identify the legacy systems that will supply data for the SAP applications and to profile the quality of the legacy data.​ | Waterfall;#Agile | 20 | 50
New | Prepare | Yes |  | Both | no | no | yes |  |  |  | Project Management​ | Project Plans Review and Validation By Team
New | Prepare | Yes |  | Both | no | no | yes |  |  |  | Project Management​ | Build an overlay of all the plans for the Release
New | Prepare | Yes |  | Both | no | no | yes |  |  |  | Project Management​ | Identify and Resolve milestone conflicts and align dependencies
New | Prepare | Yes |  | Both | no | no | yes |  |  |  | Project Management​ | Verify System Readiness for Workshops
New | Prepare | Yes |  | Both | no | no | yes |  |  |  | Project Management​ | Infrastructure and environments
New | Prepare | Yes |  | Both | no | no | yes |  |  |  | Project Management​ | Systems configuration
New | Prepare | Yes |  | Both | no | no | yes |  |  |  | Project Management​ | Data
New | Prepare | Yes |  | Both | no | no | yes |  |  |  | Project Management​ | Assess Workshops readiness
New | Prepare | Yes |  | Both | no | no | yes |  |  |  | Project Management​ | Training and templates
New | Prepare | Yes |  | Both | no | no | yes |  |  |  | Project Management​ | Support Materials Completed
New | Prepare | Yes |  | Both | no | no | yes |  |  |  | Project Management​ | Communicate & Reinforce Program documentation templates usage
2.060.020.110 | Prepare | Yes |  | Template | yes | Yes |  |  |  | In Prep & Explore in Activate | MDM | Complete the Data Migration Approach and Strategy Document | The purpose of this activity to collect input needed for the Data Migration Approach and Strategy document, in a format suitable for both communication purpose as well as for formal sign-off purpose.​ | Waterfall;#Agile | 20 | 110
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Data Definition & Governance
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Schedule MDM Data Definition & Governance and Data Migration Workshops
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | MDM | MDM Basic/Generic Training (standard concepts)
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Present MDM Data Definition & Governance and Data Migration start…
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Designate data migration/MDM roles
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Data Readiness
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Data cleansing & Data augmentation
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Data migration strategy presented to local teams
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Data Cleansing Workshops scheduled
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Data Migration Workshops scheduled
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Initial profiling of the data (using IDQ)
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | MDM | Analysis - Dormant Master Data (supplier, customer, item..)
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Testing | Finalize testing templates (test summary report, test log, traceability …
New | Prepare | Yes |  | Deployment | no | no | yes |  |  |  | Testing | Establish Entry & exit criteria (Define test entry and exit criteria for each…
2..000.000 | Prepare- Soft Launch | Yes |  | Template | yes | no |  |  |  |  | All | Prepare- Soft Launch |  | Waterfall;#Agile | 0 | 0
2..000.000 | Prepare- Soft Launch | Yes |  | Template | yes | no |  |  |  |  | All | Prepare- Full Launch
2..000.000 | Prepare- Soft Launch | Yes |  | Template | yes | no |  |  |  |  | Project Management​ | Prepare- Regular Phase Activities
2..000.000 | Prepare- Soft Launch | Yes |  | Template | yes | No |  |  |  |  | All | Team Specific Activities